## Sheet1
| BUDGET |  |  |  |  | EARNED |  |  |  | FORECAST |  | VARIANCE |  | PERCENT COMPLETE
| Original Budget |  | Scope Change | Trends | Current Budget | Schedule Earned | Actual Earned | Actual Hrs | To Date Perf | To Go Fct | Total Fct | Sched Var | Cost Var | Sched (Bud) | Actual (Bgt) | Actual (Fct)
| (A) | (B) | (C ) | (D) | (E=A+C) | (F) | (G) | (H) | (I=G/H) | (J=K-H) | (K=A+C+D) | (M=G-F) | (N=G-H) | (O=F/E) | (P=G/E) | (Q=G/K)
Code Discipline Description | A |  | B | C | D=A+B | E | F | G | H=F/G | I=J-G | J=A+B+C | K=F-E | M=F-G | N=E/D | O=F/D | P=F/J
D Area D - Facilities
Architectural | 365 | 365 |  |  | 365 | 250 | 254 | 153 | 1.6601 | 212 | 365 | 4 | 101 | 68.4932 | 69.589 | 69.589
Eng'rg Management | 7717 | 7717 | 0 | 160 | 7717 | 1233 | 1233 | 1167 | 1.0566 | 6710 | 7877 | 0 | 66 | 15.9777 | 15.9777 | 15.6532
Civil | 13909 | 14134 | 225 | 0 | 14134 | 11009 | 10856 | 7011 | 1.5484 | 7123 | 14134 | -153 | 3845 | 77.8902 | 76.8077 | 76.8077
Electrical | 3485 | 3485 |  |  | 3485 | 2815 | 2862 | 2952 | 0.96951 | 533 | 3485 | 47 | -90 | 80.7747 | 82.1234 | 82.1234
General | 1370 | 1370 |  |  | 1370 | 1091 | 988 | 781 | 1.265 | 589 | 1370 | -103 | 207 | 79.635 | 72.1168 | 72.1168
Instrumentation | 898 | 898 |  |  | 898 | 677 | 616 | 186 | 3.3118 | 712 | 898 | -61 | 430 | 75.3898 | 68.5969 | 68.5969
Mechanical | 1252 | 1552 | 300 | 0 | 1552 | 940 | 982 | 337 | 2.9139 | 1215 | 1552 | 42 | 645 | 60.567 | 63.2732 | 63.2732
Structural | 1650 | 1650 |  |  | 1650 | 1255 | 1179 | 841 | 1.4019 | 809 | 1650 | -76 | 338 | 76.0606 | 71.4545 | 71.4545
Area D Total | 30646 | 31171 | 525 | 160 | 31171 | 19270 | 18970 | 13428 | 1.4127 | 17903 | 31331 | -300 | 5542 | 61.8203 | 60.8578 | 60.5471
| BUDGET |  |  |  |  | EARNED |  |  |  | FORECAST |  | VARIANCE |  | PERCENT COMPLETE
| Original Budget |  | Scope Change | Trends | Current Budget | Schedule Earned | Actual Earned | Actual Hrs | To Date Perf | To Go Fct | Total Fct | Sched Var | Cost Var | Sched (Bud) | Actual (Bgt) | Actual (Fct)
| (A) | (B) | (C ) | (D) | (E=A+C) | (F) | (G) | (H) | (I=G/H) | (J=K-H) | (K=A+C+D) | (M=G-F) | (N=G-H) | (O=F/E) | (P=G/E) | (Q=G/K)
Code Discipline Description | A |  | B | C | D=A+B | E | F | G | H=F/G | I=J-G | J=A+B+C | K=F-E | M=F-G | N=E/D | O=F/D | P=F/J
D Area D - Facilities
Architectural | 365 | 365 |  |  | 365 | 250 | 254 | 153 | 1.6601 | 212 | 365 | 4 | 101 | 68.4932 | 69.589 | 69.589
Eng'rg Management | 7717 | 7717 | 0 | 160 | 7717 | 1233 | 1233 | 1167 | 1.0566 | 6710 | 7877 | 0 | 66 | 15.9777 | 15.9777 | 15.6532
Civil | 13909 | 14134 | 225 | 0 | 14134 | 11009 | 10856 | 7011 | 1.5484 | 7123 | 14134 | -153 | 3845 | 77.8902 | 76.8077 | 76.8077
Electrical | 3485 | 3485 |  |  | 3485 | 2815 | 2862 | 2952 | 0.96951 | 533 | 3485 | 47 | -90 | 80.7747 | 82.1234 | 82.1234
General | 1370 | 1370 |  |  | 1370 | 1091 | 988 | 781 | 1.265 | 589 | 1370 | -103 | 207 | 79.635 | 72.1168 | 72.1168
Instrumentation | 898 | 898 |  |  | 898 | 677 | 616 | 186 | 3.3118 | 712 | 898 | -61 | 430 | 75.3898 | 68.5969 | 68.5969
Mechanical | 1252 | 1552 | 300 | 0 | 1552 | 940 | 982 | 337 | 2.9139 | 1215 | 1552 | 42 | 645 | 60.567 | 63.2732 | 63.2732
Structural | 1650 | 1650 |  |  | 1650 | 1255 | 1179 | 841 | 1.4019 | 809 | 1650 | -76 | 338 | 76.0606 | 71.4545 | 71.4545
Area D Total | 30646 | 31171 | 525 | 160 | 31171 | 19270 | 18970 | 13428 | 1.4127 | 17903 | 31331 | -300 | 5542 | 61.8203 | 60.8578 | 60.5471

## Engineering Tracker
Project No. : ____________________________________ | [12 empty] | Report Date : ________________
Project Descripton : ______________________________ | [12 empty] | Week Ending : _______________
Project Location : ________________________________
Entity : ________________________________________
A/E Firm : ____________________________________
| BUDGET |  |  |  | FORECAST |  | EARNED |  |  |  | SPENT |  |  | PERCENT COMPLETE
Code Discipline Description | Original Budget | Scope Change | Trends | Current Budget | Total Fct | To Go Fct | Schedule Hrs | Earned Hrs | Sched Var | SPI | Actual Hrs | Cost Var | JHP | Sched (Bud) | Actual (Bud) | Actual (Fct)
| A | B | C | D=A+B | E=A+B+C | F=E-K | G | H | I=H-G | J=H/G | K | L=H-K | M=H/K | N=G/D | O=H/D | P=H/E
D Area D - Facilities
Architectural
Eng'rg Management
Civil
Electrical
General
Instrumentation
Mechanical
Structural
Area D Total