| Discipline | Commodity | Issue / Question | Possible Choices? Actions | Project Direction | Actions |
| --- | --- | --- | --- | --- | --- |
| General | Heavy Haul on site | Identify site heavy haul and crane crawl routes. Review location of aboveground facilities and capacity of underground facilities. | Upgrade undergrounds - heavy wall pipe, conduit encased duct banks, etc. Review manhole locations. Review overheads (e.g. pipe bridges) for crane/haul interferences. Reroute and redesign as necessary. |  |  |
| General | Preassembly | - What will be modularized off-site? | Review each major vendor PO to determine optimum degree of shop and field fabrication. |  |  |
| Civil | Concrete | Minimizing different concrete slab thicknesses | Avoid different slab thicknesses as much as possible. Make uniformly thick if practical. |  |  |
| Civil | Reinforcing Steel | Rebar standardization | Standardize sizes for bulk material purchase ordering. Avoid non-standard sizes. |  |  |
| Mechanical | Equipment | Determine equipment access and removal plan. | Review model and place path on drawings for equipment - also resolve valve access and head knockers during model review. |  |  |
| Piping | Fabrication | Do Construction, piping fabricator and support fabricator have coordinated fabrication process to manage deliveries? | Weekly release for fabrication curves and PO language |  |  |
| Electrical | Duct banks | Providing spare conduits | 4 spare conduits per run as rule of thumb |  |  |
| Electrical | Lighting | Standardizing fixture and lamp types | How many different fixture types and number of lamps? |  |  |
| Software | Model | What info in model to support Work Packaging? |  |  |  |
| Procurement | Management of Material | Will link from drawings to piece mark/part number to BPS and site storage location be easily understood? |  |  |  |

Note: This Checklist provides a limited number of examples solely for constructability suggestions