| Report No. |  |  |  |  |  |  |  |  | Date: |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name: |  |  |  |  |  |  |  |  | Project No. |  |
| System No. |  |  | Equipment Identification: |  |  |  |  | Area: |  |  |
| REFERENCE DOCUMENT No. |  | Rev. No. | REMARKS |  |  |  |  |  |  |  |
| ITEM |  |  |  |  |  | ACCEPT | N/A | REMARKS |  |  |
| - Name plate data is correct |  |  |  |  |  |  |  |  |  |  |
| - Foundation complete and anchor bolts set |  |  |  |  |  |  |  |  |  |  |
| - Pre-Installation Checks |  |  |  |  |  |  |  |  |  |  |
| - Anchor bolt locations are correct and bolts are plum with proper projection/thread length and acceptable physical condition. |  |  |  |  |  |  |  |  |  |  |
| - Foundation is properly prepared and grouted (if applicable). |  |  |  |  |  |  |  |  |  |  |
| - Concrete foundation has met minimum comprehensive strength requirements. |  |  |  |  |  |  |  |  |  |  |
| - Structural Steel supports are designed, inspected, and properly documented including painted and coated. |  |  |  |  |  |  |  |  |  |  |
| - Shims are smooth, flat, and free of dirt or foreign materials. |  |  |  |  |  |  |  |  |  |  |
| - Red plate (fixed and sliding ends) are painted and/or coated. |  |  |  |  |  |  |  |  |  |  |
| - Slide plate is lubricated, and Teflon® or similar surface is complete. |  |  |  |  |  |  |  |  |  |  |
| - Load bearing/leveling surfaces of plates, blocks, rails, sole plates are flat within tolerances |  |  |  |  |  |  |  |  |  |  |
| - Unit set on foundation |  |  |  |  |  |  |  |  |  |  |
| - Levelness of base plates, blocks, rails, sole plates, etc., and/or the equipment are within tolerances |  |  |  |  |  |  |  |  |  |  |
| - Centerline location and elevation checked |  |  |  |  |  |  |  |  |  |  |
| - Anchor bolts torqued |  |  |  |  |  |  |  |  |  |  |
| - Preliminary alignment and soft foot check complete |  |  |  |  |  |  |  |  |  |  |
| - Grouting complete |  |  |  |  |  |  |  |  |  |  |
| - Auxiliary systems (i.e. lube/seal oil, balance, cooling, hydraulic, etc.) are properly cleaned, flushed and connected |  |  |  |  |  |  |  |  |  |  |
| - Preservative compounds greases, and oils cleaned from equipment. Desiccant is removed |  |  |  |  |  |  |  |  |  |  |
| - Inspect, clean and install, or reinstall mechanical seals, packing, wipers, etc. |  |  |  |  |  |  |  |  |  |  |
| - Final alignment is complete |  |  |  |  |  |  |  |  |  |  |
| - Systems charged with specified operating fluid |  |  |  |  |  |  |  |  |  |  |
| - Provide and install temporary compressor suction strainers. |  |  |  |  |  |  |  |  |  |  |
| - Rotation of driven and driving equipment Is correct. |  |  |  |  |  |  |  |  |  |  |
| - Coupling Assembled |  |  |  |  |  |  |  |  |  |  |
| - Sheaves and belts alignment and tensioned. |  |  |  |  |  |  |  |  |  |  |
| - Instruments and controls checked |  |  |  |  |  |  |  |  |  |  |
| - Insulation complete |  |  |  |  |  |  |  |  |  |  |
| COMMENTS: |  |  |  |  |  |  |  |  |  |  |
| RESPONSIBLE ENGINEER: |  |  |  |  |  |  |  |  |  |  |
|  | (Name / Signature) |  |  |  |  |  | (Date) |  |  |  |