## Project Contracting Strategy
Project Contracting Strategy (PCS) Template
PROJECT NO: | : | <<Enter Number>> |  |  | Engineering Office |  |  | Requisition Planned Reviews |  |  | Agreement Type by Price |  |  | Tendering Methods |  |  | Critical Package |  |  |  |  | Completion Date
[5 empty] | Enter Designer Name or Department |  |  | Full = 60%, 90% & 100% Reviews |  |  | LS = Lump Sum | Low Risk- Defined Scope |  | P = Public | D = Direct Purchase |  | YES = On Project Critical Path |  |  |  |  | Enter current planned Completion Date of Agreement
KEY PERSONNEL |  |  |  | Enter the agreement title and necessery refrences scope |  |  |  | Part = 60% and 100% Reviews only |  |  | WUR= Work Unit Rate | Low Risk- Defined Scope |  | C = Contest | E = E-reserve Auction |  | NO = Not on Critical Path
CONTRACT MANAGER | : | <<Enter Name>> | Agreement Category |  | Requisition Originator | [5 empty] | Unit Rate = Unit price | Mid Risk: uncertine Quanitiy |  | F = Framework | T = Two Stages | [6 empty] | Defect Liability (Warranty) Period
ENGINEERING MANAGER | : | <<Enter Name>> | ENG = Engineering |  | Enter Originators Initials or Name |  |  | Contracts Specialist |  |  | Cost Plus= % or Fee | Hight Risk, not defined scope |  | S = Selective Tendering |  |  | Handover Requirements |  |  |  |  | State Number of Months (i.e. 12m)
CONSTRUCTION MANAGER | : | <<Enter Name>> | CON = Construction |  |  |  |  | Enter Originators Initials or Name |  |  | % of CON K |  |  | L&K = Localization & Knowledge Transfer |  |  | Typical = Preliminary then Final of Entire Works
PROJECT MANAGER | : | <<Enter Name>> | CO = Consultant |  | Requisition Responsible Department | [8 empty] | ITT Issue & Planned Award Date |  |  | Custom = Partial, Phased or staged Handover |  |  |  |  | Comments
|  |  | DB = Design & Build |  | ENG = Engineering |  |  | Budget Value | [5 empty] | Enter Date of Issue / Award | [7 empty] | Insert any relevant additional information as necessary
GUIDANCE NOTES / KEY TO DATA FIELDS |  |  |  |  | CONS = Construction |  |  | State Current Budget in SAR (m) |  |  | Sourcing Location | [5 empty] | Supplier Quality Levels for Critical Equipment
Fields in the Project Contracting Strategy shall be populated using the the categories and abbrevations contained in these guidance notes, These fields are a guide to assist in standardising the use of the Project Contracting Strategy however the responsible Director of Contracts & Procurement Department may add to or modify to suit the nature of the Works and Services an Authority intends to contract. |  |  |  |  | HSSE = Health, Safety, Security & Environment | [5 empty] | Local: Within State/County |  |  | Operational Spares |  |  | 1 = Final Surv & Ship Release
[5 empty] | O&M = Operations and Maintenance | [5 empty] | Regional: Within Country |  |  | YES = Spares required to be included |  |  | 2 = Limited Scope Supplier Quality Surveillance
[11 empty] | Global: as above + International |  |  | NO = Spares not required |  |  | 3 = Full Scope Supplier Quality Surveillance
4 = Resident Quality Survelliance
Agreement No. |  |  |  | Agreement Title / Refrence | REQUISITION RESPONSIBILITY |  |  |  |  | TENDERING INFORMATION - add selection of proper pricing. | [6 empty] | POST AWARD INFORMATION |  |  |  |  | Comments
|  |  | Agreement Category |  | Engineering Office | Responsible Department | Originator | Planned Reviews | Contract Specialist | Budget Value | Agreement Type | Tendering Methods | Sourcing Location | ITT Issue Date | Planned Award Date | Operational Spares Required | Critical Package | Handover Requirements | Supplier Quality Levels | Completion Date | Defect Liability Period