## Summary
Project Trend Form Template
|  | TREND NOTICE | [5 empty] | Trend No.
|  | Project Job Number | [5 empty] | Date:
TITLE | [7 empty] | Originator:
Discipline:
Office:
Description: | [7 empty] | Scope Change
Category 1
Category2
Reason for Change:
TREND SUMMARY:
| Costs: |  |  |  |  | Costs, k SAR |  | Jobhours
Equipment Cost:
Bulk Material:
Subcontracts:
Project Labor Cost:
Procurement Costs
Construction Cost
Engineering HO Services Cost:
Other Cost:
| SUBTOTAL |  |  |  |  | 0 |  | 0
Contingency
| GRAND TOTAL |  |  |  |  | 0 |  | 0
Schedule
| Incremental |  | Week(s) |  | Impact on MC Date |  | Week(s)
Impact |  | See above
APPROVALS:
STATUS:
| Engineering Manager |  |  | Date
| Project Controls Manager |  |  | Date
| Project Manager |  |  | Date

## Detail build up
XYZ Project Job #12345
Trend No.
Description:
NEW SCOPE
ITEM | D044 |  |  | UNIT COST |  |  | CONSTRUCTION COST |  |  | TOTAL COST |  |  | TOTAL
NO. | CODING | DESCRIPTION/PARAMETERS | QTY | UNIT | MAT'L | S/C | HR/UNIT | SAR/ UNIT | TOTAL | MAT'L | LABOR | S/C | COST
1 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
2 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
3 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
4 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
5 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
6 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
7 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
8 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
9 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
10 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
11 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
12 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
13 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
14 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
15 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
16 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
17 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
18 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
19 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
20 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
21 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
22 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
23 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
24 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
25 | [7 empty] | 0 |  | 0 | 0 | 0 | 0
| TOTAL TREND SCOPE | [8 empty] | 0 | 0 | 0 | 0