## Project Dashboard (hidden)
CAPEX PROGRAMME
[5 empty] | ### PROJECT NAME ### | [13 empty] | Schedule | >14 days +ve float |  | 14 | REMEMBER TO CHANGE THE GRAPH RANGES EACH MONTH!!!
[5 empty] | Mashroat / Entity Project Numbers: XXX / YYYYY | [13 empty] | Legend: | <14 days +ve float |  |  | because we do not want blanks in the chart
[5 empty] | Report Period End: XXXXXXXXXXXXX | [14 empty] | zero or -ve float |  | 0
[23 empty] | Q5 Project Cost Graph Data - cumulative | [6 empty] | Q5 Project Cost Graph Data - incremental
EPMO Project Team Members | PMC Manager | XXX | Senior Field Engineer | XXX | Cost Engineer | XXX | Contract Admin. | XXX | Planner | XXX | EPMO Manager | XXX | Project Key Milestones |  |  |  | Baseline | Current Budget | Forecast / Actual | F / A | Variance (days) |  | Month | Reported Current Budget | Reported AFC | Planned Value (BCWS) | Earned Value (BCWP) | Actual Costs (ACWP) | Fcst Spend to complete (ETC) | Month | Planned Value (BCWS) | Earned Value (BCWP) | Actual Costs (ACWP) | Fcst Spend to complete (ETC) | Cumulative CPI | Cumulative SPI | Incremental CPI | Incremental SPI
[23 empty] | 2010-01-01 | 35000000 | 40335559.54 | 1000000 | 800000 | 1200000 | 1200000 | 2010-01-01 | 1000000 | 800000 | 1200000 |  | 0.66667 | 0.8 | 0.66667 | 0.8
Summary Project Scope: |  |  | Stage: |  | Gate No. | XXX | [6 empty] | Commence Landside Road |  |  |  |  | 2010-04-23 | 2010-04-23 | A | 0 |  | 2010-02-01 | 35000000 | 40335559.54 | 2000000 | 1600000 | 2400000 | 2400000 | 2010-02-01 | 1000000 | 800000 | 1200000 |  | 0.66667 | 0.8 | 0.66667 | 0.8
XXX | [12 empty] | Complete Apron PQC |  |  |  |  | 2010-05-28 | 2010-06-04 | A | -7 |  | 2010-03-01 | 35000000 | 40257306.73 | 3000000 | 2400000 | 3600000 | 3600000 | 2010-03-01 | 1000000 | 800000 | 1200000 |  | 0.66667 | 0.8 | 0.66667 | 0.8
[13 empty] | EDF Commence Stand LV Feeds |  |  |  |  | 2010-06-09 | 2010-05-10 | A | 30 |  | 2010-04-01 | 35000000 | 32000000 | 4000000 | 3200000 | 4800000 | 4800000 | 2010-04-01 | 1000000 | 800000 | 1200000 |  | 0.66667 | 0.8 | 0.66667 | 0.8
[13 empty] | Fuel Hydrants Operational |  |  |  |  | 2010-06-30 | 2010-08-13 | F | -44 |  | 2010-05-01 | 35000000 | 39918656.11 | 5000000 | 4000000 | 6000000 | 6000000 | 2010-05-01 | 1000000 | 800000 | 1200000 |  | 0.66667 | 0.8 | 0.66667 | 0.8
Project ESS&H Status: | Hours Worked (month) |  |  | Cumulative Hours Worked: |  |  | LTI's this period |  | LTI's ITD |  | Rolling AFR: |  | Stands Operational |  |  |  |  | 2010-07-01 | 2010-07-01 | A | 0 |  | 2010-06-01 | 35000000 | 39635558 | 6000000 | 4800000 | 7200000 | 7200000 | 2010-06-01 | 1000000 | 800000 | 1200000 |  | 0.66667 | 0.8 | 0.66667 | 0.8
[13 empty] | Phase 1 Complete |  |  |  |  | 2010-08-06 | 2010-08-20 | F | -14 |  | 2010-07-01 | 35000000 | 39635558 | 7000000 | 5600000 | 8400000 | 8400000 | 2010-07-01 | 1000000 | 800000 | 1200000 |  | 0.66667 | 0.8 | 0.66667 | 0.8
[13 empty] | Trigger - Phase 1 |  |  |  |  | 2010-06-30 | 2010-06-30 | F | 0 |  | 2010-08-01 | 35000000 | 39635558 | 8000000 | 6400000 | 9600000 | 9600000 | 2010-08-01 | 1000000 | 800000 | 1200000 |  | 0.66667 | 0.8 | 0.66667 | 0.8
[13 empty] | Trigger - Phase 2 |  |  |  |  | 2010-11-28 | 2010-11-28 | F | 0 |  | 2010-09-01 | 35000000 | 39635558 | 9000000 | 7200000 | 10800000 | 10800000 | 2010-09-01 | 1000000 | 800000 | 1200000 |  | 0.66667 | 0.8 | 0.66667 | 0.8
Project Status and Work Undertaken This Period: | [12 empty] | Milestone & Trigger status: | [9 empty] | 2010-10-01 | 35000000 | 39635558 | 8200000 | 8200000 | 12000000 | 12000000 | 2010-10-01 | -800000 | 1000000 | 1200000 |  | 0.68333 | 1 | 0.83333 | -1.25
[23 empty] | 2010-11-01 | 35000000 | 39635558 | 9200000 |  |  | 13200000 | 2010-11-01 | 1000000 |  |  | 1200000
[23 empty] | 2010-12-01 | 35000000 | 39635558 | 10200000 |  |  | 14400000 | 2010-12-01 | 1000000 |  |  | 1200000
[23 empty] | 2011-01-01 | 35000000 | 39635558 | 11200000 |  |  | 15600000 | 2011-01-01 | 1000000 |  |  | 1200000
[23 empty] | 2011-02-01 | 35000000 | 39635558 | 12200000 |  |  | 16800000 | 2011-02-01 | 1000000 |  |  | 1200000
[23 empty] | 2011-03-01 | 35000000 | 39635558 | 13200000 |  |  | 18000000 | 2011-03-01 | 1000000 |  |  | 1200000
Key Issues and Risks Discussion: | [12 empty] | Work Forecast Next Period: | [9 empty] | 2011-04-01 | 35000000 | 39635558 | 14200000 |  |  | 19200000 | 2011-04-01 | 1000000 |  |  | 1200000
[23 empty] | 2011-05-01 | 35000000 | 39635558 | 15200000 |  |  | 20400000 | 2011-05-01 | 1000000 |  |  | 1200000
[23 empty] | 2011-06-01 | 35000000 | 39635558 | 16200000 |  |  | 21600000 | 2011-06-01 | 1000000 |  |  | 1200000
[23 empty] | 2011-07-01 | 35000000 | 39635558 | 17200000 |  |  | 22800000 | 2011-07-01 | 1000000 |  |  | 1200000
[23 empty] | 2011-08-01 | 35000000 | 39635558 | 18200000 |  |  | 24000000 | 2011-08-01 | 1000000 |  |  | 1200000
Project Key Cost Information (further detail available): | [6 empty] | CIP (xxx-xx): |  | xxx |  | Commercial Commentary: |  |  |  | Main Contract Type: ……………….. | [7 empty] | 2011-09-01 | 35000000 | 39635558 | 19200000 |  |  | 25200000 | 2011-09-01 | 1000000 |  |  | 1200000
Cost breakdown | Baseline Budget | Approved Changes | Current Budget | Authorised Funding | Committed | Pending Changes / Trends | Estimate at Completion | ACWP (Actual) | BWCP (Earned) | BCWS (Planned) | [12 empty] | 2011-10-01 | 35000000 | 39635558 | 20200000 |  |  | 26400000 | 2011-10-01 | 1000000 |  |  | 1200000
(SAR '000s) | [7 empty] | ITD | ITD | ITD | [12 empty] | 2011-11-01 | 35000000 | 39635558 | 21200000 |  |  | 27600000 | 2011-11-01 | 1000000 |  |  | 1200000
Land & Studies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 2011-12-01 | 35000000 | 39635558 | 22200000 |  |  | 28800000 | 2011-12-01 | 1000000 |  |  | 1200000
Design Consultants | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 2012-01-01 | 35000000 | 39635558 | 23200000 |  |  | 30000000 | 2012-01-01 | 1000000 |  |  | 1200000
Construction Contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PM/Supervision | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 2012-02-01 | 35000000 | 39635558 | 24200000 |  |  | 31200000 | 2012-02-01 | 1000000 |  |  | 1200000
Specialized Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CPI/SPI and Percent Complete Variance Commentary: | [11 empty] | 2012-03-01 | 35000000 | 39635558 | 25200000 |  |  | 32400000 | 2012-03-01 | 1000000 |  |  | 1200000
Risk & Contngency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Escalation & other costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 2012-04-01 | 35000000 | 39635558 | 26200000 |  |  | 33600000 | 2012-04-01 | 1000000 |  |  | 1200000
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 2012-05-01 | 35000000 | 39635558 | 27200000 |  |  | 34100000 | 2012-05-01 | 1000000 |  |  | 500000
[23 empty] | 2012-06-01 | 35000000 | 39635558 | 28200000 |  |  | 34600000 | 2012-06-01 | 1000000 |  |  | 500000
Previous Period Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 2012-07-01 | 35000000 | 39635558 | 29200000 |  |  | 35100000 | 2012-07-01 | 1000000 |  |  | 500000
Period Movement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 2012-08-01 | 35000000 | 39635558 | 30200000 |  |  | 35600000 | 2012-08-01 | 1000000 |  |  | 500000
[23 empty] | 2012-09-01 | 35000000 | 39635558 | 31200000 |  |  | 36100000 | 2012-09-01 | 1000000 |  |  | 500000
Major Packages | CPI (Actual/Earned) |  | SPI (Actual/Planned) |  | Percent Complete | [5 empty] | Compensation Events (SAR '000S) |  | RfCO | CN's (Value) |  |  | CN's (qty) | [5 empty] | 2012-10-01 | 35000000 | 39635558 | 32200000 |  |  | 36600000 | 2012-10-01 | 1000000 |  |  | 500000
| Q5 ITD | Cur.Per. | Q5 ITD | Cur.Per. | Planned | Actual | ITD Delta | Plan Per. | Actual Per. |  |  |  | Total | Implem | Notified | Total | Implem | Notified | Total |  |  |  | 2012-11-01 | 35000000 | 39635558 | 35000000 |  |  | 37100000 | 2012-11-01 | 2800000 |  |  | 500000
[Design Contract #1] | [10 empty] | [Design Contract #1] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2012-12-01 |  | 39635558 |  |  |  | 37600000 | 2012-12-01 |  |  |  | 500000
[Design Contract #2] | [10 empty] | [Design Contract #2] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-01-01 |  | 39635558 |  |  |  | 38100000 | 2013-01-01 |  |  |  | 500000
[Construction Contract #1] | [10 empty] | [Construction Contract #1] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-02-01 |  | 39635558 |  |  |  | 38600000 | 2013-02-01 |  |  |  | 500000
[Construction Contract #2] | [10 empty] | [Construction Contract #2] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-03-01 |  | 39635558 |  |  |  | 39100000 | 2013-03-01 |  |  |  | 500000
[Construction Contract #3] | [10 empty] | [Construction Contract #3] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-04-01 |  | 39635558 |  |  |  | 39635558 | 2013-04-01 |  |  |  | 535558
TOTAL PROJECT | [10 empty] | TOTAL PROJECT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013-05-01 | [6 empty] | 2013-05-01
Quality Commentary:
[26 empty] | TRUE |  |  | TRUE
[25 empty] | Planned Value at completion = Current Budget, correct |  |  | Forecast at completion = AFC, correct
QTS (Quantity Tracking)
[11 empty] | Quality Metrics |  | NCR's (qty) |  |  | Open Aging |  | Avg Time to Close |  |  | Procurement Plan
[13 empty] | Open | Closed | Total | > 30 days | > 60 days |  |  |  | Construction Programme
[11 empty] | [Construction Contract #1] |  | 0 | 0 | 0 | [5 empty] | Risk & Opps Registers
[11 empty] | [Construction Contract #2] |  | 0 | 0 | 0 | [5 empty] | CE Register
[11 empty] | [Construction Contract #3] |  | 0 | 0 | 0 | [5 empty] | EW Register
[11 empty] | TOTAL PROJECT |  | 0 | 0 | 0 | [5 empty] | Trend Reports
DATA FOR ILLUSTRATION PURPOSES ONLY
ENTITY & EPMO/PMC LOGO
HERE
DATA FOR ILLUSTRATION PURPOSES ONLY

## EPM-KPC-TP-000039-AR
التقرير التفصيلي والموجز للتكلفة الشاملة
| الميزانية وضبط الميزانية |  |  |  | الالتزام والتوقعات | [5 empty] | التباين | التكلفة والقيمة حتى تاريخه
عنوان الوثيقة | الميزانية الأصلية | تغييرات النطاق التي وافق عليها العميل | الميزانية الحالية | التمويل المصرح به حتى تاريخه | ترسية العقد | أوامر التغيير المنفّذة | قيمة العقد الحالية | التغييرات أو التوجّهات قيد التنفيذ | غير ملتزم | التقدير عند الاكتمال | الميزانية الحالية ناقص التقدير عند الاكتمال | معتمد | متراكم | التكلفة الفعلية للعمل المنجز التكلفة الفعلية للعمل المنجز | ميزانية التكلفة الفعلية للعمل المنجز ميزانية التكلفة الفعلية للعمل المنجز | ميزانية التكلفة الفعلية للعمل المجدول ميزانية التكلفة الفعلية للعمل المجدول | المدفوع
وصف عنصر التكلفة | مليون ريال سعودي | مليون ريال سعودي | مليون ريال سعودي | مليون ريال سعودي | مليون ريال سعودي | مليون ريال سعودي | مليون ريال سعودي | مليون ريال سعودي | مليون ريال سعودي | مليون ريال سعودي | مليون ريال سعودي | مليون ريال سعودي | مليون ريال سعودي | مليون ريال سعودي | مليون ريال سعودي | مليون ريال سعودي | مليون ريال سعودي
1. حيازة الأراضي | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. الدراسات والمسوحات والاستشارات المتخصصة | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
210 - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220 - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. إدارة المشروع، إدارة التشييد والإشراف في الموقع | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
310 - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
320 - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. خدمات التصميم | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
410 - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
420 - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. التشييد | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
510 - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
520 - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. المعدات والمواد المتخصصة التي تشتريها الجهة العامة | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
610 - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
620 - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. الدعم المقدم من الجهة العامة للإنجاز | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
710 - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
720 - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. المخاطر وحالات الطوارئ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
810 - تقييم التعرض للمخاطر | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
820 - حالات الطوارئ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9- مخاطر الزيادات في التكاليف / التضخم / سعر الصرف | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
910 - الزيادات في التكاليف / التضخم | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
920 - سعر الصرف | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
إجمالي تكلفة المشروع | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
المستوى - 3-E - خارجي تخرج الوثائق الإلكترونية عن نطاق ضبط ورقابة المؤسسة بمجرد طباعتها على الورق، وقد تُصبح غير محدثة. لذا، يُرجى الرجوع إلى نظام إدارة المحتوى المؤسسي للاطلاع على أحدث نسخة.
EPM-KPC-TP-000039-AR Rev.001
Note on E15: Stokes, Simon [NPMO]: Costs associated with the purchase of the land necessary for the construction of the project. Includes all associated professional fees and charges. Can be subsequently expressed as a SAR cost / m2.
Note on E20: Stokes, Simon [NPMO]: Costs associated with technical or consulting services for studies (feasibility, market, financial), investigations (geotechnical, surveying testing, topographic, environmental impact), specialist advice or the like that are necessary to support the approval, permitting, design or other front end requirements for the project.
Note on E25: Stokes, Simon [NPMO]: Costs associated with the provision of professional project management (PM), construction management (CM) and site supervision services using specialized techniques to oversee the planning, design, and construction of a project, from its beginning to its end, including inspection and acceptance.
Note on E30: Stokes, Simon [NPMO]: Costs associated with the performance of design services for the project.
Note on E35: Stokes, Simon [NPMO]: Costs associated with the construction of permanent Works (e.g. buildings, either residences, commercial, or institutional structures, as well as construction activities such as paving, highway construction, utility construction and landscape installation). Includes the costs of all works, both temporary and permanent, equipment and facilities and items as such, procured and performed by the appointed construction contractor(s).
Note on E40: Stokes, Simon [NPMO]: Costs associated with the purchase and provision by the Entity directly of specialized equipment, material, fittings, devices, appliances, apparatus, machinery, including business equipment, movable furniture and small operating equipment, and the like which are to be incorporated into and used within the finished project.
Note on E45: Stokes, Simon [NPMO]: Costs associated with the provision by the Entity directly of support to the delivery, including items such as insurance, permits, licenses, royalties, taxes, fees, utilities, facilities, site access and other such entity incurred costs.
Note on E51: Stokes, Simon [NPMO]: Cost allowance included for identified (e.g. known) and foreseeable risks. Generally, Risk is a condition or event that have the potential to occur (or not occur) and impact the project cost and schedule. The amount to be included here is the sum of the evaluated risk exposure for each of the identified risks.
Note on E52: Stokes, Simon [NPMO]: Cost allowance included to provide for uncertainties (e.g. unknown) in quantity, pricing, productivity, activity duration, and timing that lie within the defined scope of the project, to the extent that these items are not identified as specific risks above.
Note on E56: Stokes, Simon [NPMO]: Escalation is a provision in the capital cost estimate to cover the forecast increase in the capital cost from the estimate base date up to the completion of the project. In other words, it is a cost allowance included to cover the foreseeable increase in the basic cost of goods, equipment, materials and services required for the Project that may occur from the base date of an estimate or forecast to the time when the material is purchased or delivered or the service is performed. Escalation generally relates to the price trends occurring in a given segment of the industry. Inflation is the aggregate average of a large number of changing prices and costs throughout the economy. The estimate should identify the costs to be incurred over the timeframe of the project in order to identify and address the exposure and risk to final outturn costs from the specific escalation or general inflation indices used.
Note on E57: Stokes, Simon [NPMO]: Costs associated with foreign currency exchange, if required, are to address the costs of currency hedging where expenditure may be in a currency other than the project base currency (e.g. SAR). The estimate should identify the costs to be incurred in each currency in order to identify and address the exposure and risk to final outturn costs from the differing currencies to be used.

## Sheet1 (hidden)
Level 1 | Level 2 | Level 3 | Level 4 | Level 5a | Level 5b | Level 5c | Level 6a | Level 6b | Level 7
|  |  |  | Cost - Stem1 (Natural Class) | Contractor | Contract Goods & Services designator | Facility / Location / Project element | WBS | Commodity
Entity | 000 - neutral | 000 - neutral | Project number | 1xx - Land | Single character code in SDN | Single character code in SDN | xx - neutral |  | Standard Construction COA or by CSI Masterformat …
| If used … | If used … | 11 characters | 2xx - Studies | 1 | 1 | If used …
| Region | Sub-Region | 18MOTG00001 | 3xx - Project Management | 2 | 2
| Sector | Sub-Sector |  | 4xx - Design services
5xx - Construction
| Year of Project approval | Budget year | 18 | 6xx - Site Supervision
| Entity | Organisation | MOT | 7xx - Specialist Equipment
| Government / Private? | Sector code | G / P | 8xx - Risk & Contingency
|  | Sequence no | 00001 | 9xx - Escalation / inflation / currency risk